## Sheet3
Duration | Count of Task Name
1 month | 2
2 months | 2
2 weeks | 2
(blank) | 2

## Sheet1
Task Name | Start Date | Duration
Project Intitation | 2023-01-01
User Interface Redesign | 2023-02-01 | 2 months
Feature Development | 2023-04-01 | 2 months
Technology Stack Updated | 2023-06-01 | 1 month
User Testing and Feedback | 2023-07-01 | 1 month
Quality Assurance and Testing | 2023-08-01 | 2 weeks
Marketing and Promotion | 2023-08-15 | 2 weeks
Project Closure | 2023-09-01